## SIMP2-SFT-XX-XX-TP-Z-0004
<Add required project information in below cells> |  | Template 4 - Project Handover Checklist |  |  | Standard Information Management Plan V2
SIMP2-SFT-XX-XX-TP-Z-0004-S2-P01
This template provides a baseline checklist of actions and information to be delivered prior and up to project handover. The action list is derived from BSRIA BG79 and CIBSE doc M guidance and should be reviewed, refined/ evolved by the client (appointing party) to suit their organisational and/ or project delivery requirements.
Source <Ref only, hide column before issuing> | Project reference | Project Handover Action | Party assignment for action delivery | Action completed & information delivered? | Handover info checked & approved by client? | Additional comments
|  |  | <picklist> | <picklist> | <picklist> |  | Picklists
|  | Approvals |  |  |  |  | Architect | YES
BSRIA BG79_ 5 & CIBSE_M_ M_10 | 1 | Have the relevant authoritative bodies been approached to determine any necessary inspections/approvals? This may include Building Control, the local Planning Authority, Health and Safety Executive and the Fire Authority. | TBC | TBC | TBC |  | MEP Eng | NO
|  | < add new row for each additional action > |  |  |  |  | Struct Eng | TBC
|  | Compliance and equipment certification |  |  |  |  | Contractor | NA
BSRIA_BG79_ 6 & CIBSE_M_ 18 | 2 | Have licenses been obtained for the storage of hazardous chemicals (if necessary)? | TBC | TBC | TBC |  | Client
BSRIA_BG79_ 13 & CIBSE_M_ 4 | 3 | Have all required statutory examinations taken place? (e.g. fire systems, means of escape, pressure systems, emergency lighting, lifts, lifting equipment). | TBC | TBC | TBC |  | TBC
BSRIA_BG79_ 9 & CIBSE_M_ 25 | 4 | Have all the required test certificates been issued? | TBC | TBC | TBC |  | x
| 5 | Has a certificate of practical completion been issued? | TBC | TBC | TBC |  | x
< add new row for each additional action >
Testing
CIBSE_M_ 1 | 6 | Have all air pressure leakage testing been satisfactorily completed to Building Regulations? | TBC | TBC | TBC
| 7 | Has any required acoustic testing been satisfactorily completed and recorded? | TBC | TBC | TBC
< add new row for each additional action >
Commissioning
CIBSE_M_ 12 | 8 | Have pre-commissioning cleaning of the heating, ventilating and air conditioning systems been carried out? | TBC | TBC | TBC
CIBSE_M_ 33 | 9 | Has any re-lamping, filter changing and cleaning taken place as required by the specification? | TBC | TBC | TBC
CIBSE_M_ 22 | 10 | Have all utility supplies been inspected, approved and signed off? | TBC | TBC | TBC
CIBSE_M_ 27 | 11 | Has water treatment appropriate to the installed services been carried out? | TBC | TBC | TBC
BSRIA_BG79_ 7 & CIBSE_M_ 2 | 12 | Has all the commissioning work been completed, and any contractual obligations regarding witnessing of commissioning and testing work inc. appropriately signed witnessing documentation been provided? | TBC | TBC | TBC
BSRIA_BG79_ 8 & CIBSE_M_ 3 | 13 | Have commissioning reports and associated information been issued? | TBC | TBC | TBC
< add new row for each additional action >
Completion
CIBSE_M_ 6 | 14 | Have all failure defect and deficiency inspections been conducted and any required works been recorded and agreed? | TBC | TBC | TBC
BSRIA_BG79_ 15 & CIBSE_M_ 34 | 15 | Have the listed outstanding defects been rectified to acceptable standards? | TBC | TBC | TBC
BSRIA_BG79_ 11 & CIBSE_M_ 20 | 16 | Has any schedule of outstanding works (snagging) been agreed? | TBC | TBC | TBC
BSRIA_BG79_ 12 & CIBSE_M_ 21 | 17 | Have any additional works that are required been arranged? | TBC | TBC | TBC
BSRIA_BG79_ 18 & CIBSE_M_ 32 | 18 | Has the health and safety file been compiled, checked and issued? | TBC | TBC | TBC
CIBSE_M_ 28 | 19 | Has all warranty documentation been issued? | TBC | TBC | TBC
CIBSE_M_ 29 | 20 | Have completed O&M manuals and record drawings been issued and approved? | TBC | TBC | TBC
CIBSE_M_ 31 | 21 | Have any waste/surplus materials been removed from the site? | TBC | TBC | TBC
< add new row for each additional action >
Record
CIBSE_M_ 14 | 22 | Has the construction design management contractor (CDMC) issued general details of the structure’s equipment, maintenance facilities and procedures, construction methods and materials for inclusion in the health and safety file? | TBC | TBC | TBC
BSRIA_BG79_ 17 | 23 | Have the record drawings been issued and checked? | TBC | TBC | TBC
| 24 | Have written confirmations of completion been issued by designers, consultants, contractor etc? | TBC | TBC | TBC
BSRIA_BG79_ 16 & CIBSE_M_ 30 | 25 | Have all the required tools, spares, and consumables been issued, and an inventory provided? | TBC | TBC | TBC
| 26 | Have the required number of key and fobs copies, correctly labelled and included within an inventory list been provided? | TBC | TBC | TBC
CIBSE_M_ 35 | 27 | Have all handover meter readings and fuel stocks been recorded and issued? | TBC | TBC | TBC
< add new row for each additional action >
Project assurance
CIBSE_M_ 5 | 28 | Has the client been informed of any likelihood of change to the scheduled completion date? | TBC | TBC | TBC
CIBSE_M_ 16 | 29 | Has the inspection of works commenced in accordance with an inspection policy and programme? | TBC | TBC | TBC
CIBSE_M_ 19 | 30 | Are on-going inspections being carried out in accordance with any inspection policy? | TBC | TBC | TBC
CIBSE_M_ 26 | 31 | Have all final inspections been completed and evidenced, as required? | TBC | TBC | TBC
| 32 | Has the quality report been completed to reflect the final completion and issued? | TBC | TBC | TBC
| 33 | Have all project warranties been issued? | TBC | TBC | TBC
< add new row for each additional action >
Asset strategy, planning and management
CIBSE_M_ 8 | 34 | Is the client fully aware of their post-handover obligations including the need to arrange insurances and contracts for maintenance during the defects period to ensure asset warranties are maintained? | TBC | TBC | TBC
CIBSE_M_ 11 | 35 | Has the client been consulted regarding the format and required procedures for the handover meeting(s)? | TBC | TBC | TBC
CIBSE_M_ 15 | 36 | Is all project information and O&M manuals to be handed over being/ been assembled and the programme is in place to review and accept? | TBC | TBC | TBC
BSRIA_BG79_ 3 & CIBSE_M_ 9 | 37 | Have arrangements been made to recruit O&M personnel as required? | TBC | TBC | TBC
BSRIA_BG79_ 1 | 38 | Has a building services maintenance contract been arranged, including a contractual requirement to maintain and upkeep the O&M manual and asset record information? (this applies to in-house departmental agreements or 3rd party maintenance appointments) | TBC | TBC | TBC
BSRIA_BG79_ 2 | 39 | Has all necessary insurance(s) been arranged? | TBC | TBC | TBC
BSRIA_BG79_ 4 & CIBSE_M_ 17 | 40 | If required, has an engineer been appointed to assist during the initial period of occupation? | TBC | TBC | TBC
CIBSE_M_ 13 | 41 | Have all utilities suppliers been selected, tariffs for the utility supplies negotiated and a contract with a meter operator arranged? | TBC | TBC | TBC
CIBSE_M_ 23 | 42 | Have all operator training and demonstration sessions taken place, with details of those in attendance and certificates of competence awarded recorded? (as appropriate) | TBC | TBC | TBC
CIBSE_M_ 24 | 43 | Have occupant demonstrations, training sessions and any targeted user guides been compiled and issued ? (as required) | TBC | TBC | TBC
< add new row for each additional action >
Asset life cycle cost
|  | < add new row for each additional action > | TBC | TBC | TBC
Emergency strategy
BSRIA_BG79_ 14 | 44 | Have the fire systems and means of escape been inspected and approved? Has a fire risk assessment been undertaken? | TBC | TBC | TBC
< add new row for each additional action >
Asset risk management
< add new row for each additional action >
The SFT master workbook, appendices and templates are licensed under the Creative Commons Attribution-NonCommercial-NoDerivatives 4.0 International (CC BY-NC-ND). To view a copy of this license, visit https://creativecommons.org/licenses/by-nc-nd/4.0/legalcode |  |  | Status Code: <e.g. S2> | Revision: <e.g. P01> | Name: <e.g. SCHOOL ABC>
|  |  | Revsion Date : <xx/xx/xxxx> | Revision Authors Initials: <XXX> | Unique ID/ name: <e.g. SCHOOL-ABC-XX-XX-TP-Z-0002>