Client project information manager

Scope of Services

Invitation to Tender (ITT)

[Insert Project Name]

[Insert Contracting Authority/ Organisation]

[Revision]

[Date]

Background

This document has been produced in response to the development of the SFT Standard information management plan (SIMP) for public sector bodies in Scotland.

This document offers a best practice approach to the procurement of client project information management services in accordance with BS EN ISO 19650 parts 1 and 2 – Information management using BIM, on new public sector projects.

Document reference: SIMP-SFT-XX-XX-SC-Z-0001

Status: S2- Suitable for information

Revision: P04

Date: November 2025

Terms of Use

This document has been developed by Scottish Futures Trust and all copyright, trademarks and other intellectual property rights in this document are owned by and vest solely in Scottish Futures Trust. The document has been prepared by Scottish Futures Trust on a non-reliance basis and thus is not advice. It does not absolve any recipient or user from its responsibility to conduct its own investigations and procure its own advice – legal, financial, technical, commercial, or otherwise as they see fit – to the validity and viability of the document. Scottish Futures Trust accepts no liability for any losses (including any indirect or consequential loss), including but not limited to loss of business or profits or any other financial or material loss arising out of or in any way connected with the use of, or inability to use, this document by any recipient or user. Scottish Futures Trust disclaims all responsibility for the consequences of any recipient’s reliance on this document or for any decisions made or not made which are based upon this. Where this document contains web links to external resources, SFT take no responsibility for their content.

Preparation Guidance

Context on the role

This Invitation to Tender (ITT) outlines the scope of services for the delivery of project information management services to support the client organisation/ contracting authority during the project delivery phases. Dependant on the level of expertise and experience available, the appointment can be with a 3rd party BIM/ Information management consultant, or an additional service to an existing project party appointment. The skill set and experience required is focused on information management using BIM in accordance with BS EN ISO 19650 parts 1 and 2 – there is no design responsibility or design liability.

This scope of service does not cover BIM co-ordinator duties, which typically undertakes coordination and clash detection in connection with 3D models. Coordination and clash detection are part of the design coordination activities undertaken by the design team lead and is excluded from this scope.  The following scope of services should be reviewed against the Project information protocol to ensure alignment. Where a client organisation/ contracting authority has specific templates, these can be referred to within section 3.3 herein.

This template document assumes that all text in blue italics is guidance and should be deleted from the final ITT. All [red text] requires population by the user in the development of the ITT.

BIM readiness prior to tendering a client project information manager

Please note that this client project information manager scope of services template has been developed on the assumption that the client organisation/ contracting authority has already begun to develop a project BIM strategy, related BIM documentation and the adoption  of the  SFT Standard information management plan (SIMP). The SIMP project information strategy dashboard should be initially completed and included within Appendix C of this ITT before issuing to prospective tenderers.

It is the role of the client information manger to assist authorities and internal asset management teams to establish appropriate, project and asset information requirements for inclusion within the SIMP. Appointing a client information manager late will increase the risk of the projects information requirements not being clearly defined and included within project teams scopes and contracts.

Further guidelines are available within the Project Information Handover Initiative document available on the SFT BIM Portal [LINK]

Contents

- Introduction

- Submission of ITT Response

- Project Details and Definitions

- Scope of Works

- Quotation Submission Requirements and Evaluation Criteria

- Fee Proposal

Appendices

Appendix A		SIMP resource arrangement

Appendix B 		Information management assignment matrix

Appendix C		Project information strategy dashboard

Appendix D		Terms & Conditions

# Introduction

This invitation to tender (ITT) outlines the scope for the provision of professional client/ contracting authority project information management services for the [insert project name] on behalf of [insert organisations name]

Scottish Government is committed to embedding and realising the recommendations of the “Review of Scottish Public Sector Procurement in Construction”. The review committed that:

“BIM will be introduced in central government with a view to encouraging adoption across the public sector. The objective should be that, where appropriate, projects across the public sector adopt BIM level 2 by April 2017.”

The services required and provided shall be in accordance with BS EN ISO 19650 parts 1 and 2: information management using BIM standards and processes. Further details and resources can be found via the SFT BIM Portal: https://bimportal.scottishfuturestrust.org.uk/ and the UK Information Management Initiative Framework website https://imiframework.org/

- Submission of ITT Response

Tenderers must submit their tender responses no later than [XX.XX] on [XX/XX/XXXX] electronically to [XXXX]. Any tender response not received in full by this deadline may be rejected. [insert organisations name] may at its own discretion extend this closing date and the time for receipt of tender responses. Any extension granted under this paragraph will apply to all tenderers.

Tender responses should remain open for acceptance for a period of XX days from the deadline for receipt of responses specified above.  A tender response valid for a shorter period may be rejected.

- Project Details and Definition

  - Project Summary

| Project Data |  |
| --- | --- |
| Project Name | Insert name of project |
| Project Description | e.g. text description taken from NPR |
| Project Address | Name, Address and Postcode |
| Correspondence Address | Name, Address and Postcode |
| Procurement approach | e.g. traditional, DB, DBFM |
| Project Value | £ (value) – note also if this is net or gross |
| Contract Type | e.g. NEC3 |
| Plan of Works | e.g. RIBA 2013, GRIP etc. |
| Relevant project stage(s) | e.g. RIBA Stage 2-6 |
| Estimated number of Info delivery milestones | [from initial completion of dashboard by client] |
| Estimated number of lead appointed party’s | [from initial completion of dashboard by client] |
| Procurement Timetable, Key Dates and Meetings The planned timescales for this information management procurement exercise are as follows: |  |
| Confirm intention to quote | xx/xx/xxxx |
| Last date for queries | xx/xx/xxxx |
| Submission date | xx/xx/xxxx |
| Evaluation and select supplier | xx/xx/xxxx |
| Initial meeting with selected supplier | xx/xx/xxxx |
| Commission commences | xx/xx/xxxx |
| Commission completed | xx/xx/xxxx |
| [Insert any regular meetings that the supplier should attend and frequency / location of same] | xx |
| [If CDE platform hosting services are required from the project information manager key associated dates / time periods should be established here if known, e.g. mobilisation, archive period for storing data post-handover] | xx |
| Named contact for this procurement is: |  |
| Name | xx |
| Address | xx |
| Telephone | xx |
| E-Mail | xx |

  - Definitions

Lead appointed party: an ISO 19650 term for a provider of information concerning works, goods, or services. The lead appointed party is directly appointed by the appointing party. Examples include Architect, Engineer, Project Manager, Contractor.

Appointing party: an ISO 19650 term for a receiver of information concerning works, goods or services from a lead appointed party. This is typically, but not limited to be the client / contracting authority, employer, or owner.

Appointed party: an ISO 19650 term for a party appointed on a project to provide information concerning works, goods or services. The appointed party is directly appointed by the lead appointed party. Examples include specialist sub-consultants and/ or sub-contractors.

Common data environment (CDE): a process workflow and digital solution which enables the management of information (information containers) during the delivery and asset management stages of a project. During the delivery phase the CDE solution and workflow support the information management process and the development of a federated information model in accordance with ISO 19650-2, clause 5.6, 5.7, and the National Annex NA.

Information container: information file (e.g. model, document, table, schedule) or a sub-set of a information file (e.g. chapter, section, layer, symbol)

Information delivery milestones are established deadlines (dates) by the appointing party for required information deliverables, aligned to the project’s plan of work (stages) and key decision points.

Information standard: means BS EN ISO 19650-1 and BS EN ISO 19650-2 as may be amended or superseded from time to time.

Project information protocol: an agreement (legal contract) between an appointing party and a lead appointed party and included within each appointment. The project information protocol is also included within all lead appointed party sub-appointments throughout the delivery team(s).

Project information requirements (PIR): defined by the appointing party to establish the information needed to answer or inform high level strategic objectives in relation to the purpose, design and construction of an asset. They are identified from both project and asset management processes and inform the exchange information requirements. A set of information requirements are prepared for each appointing party key decision points.

Asset information requirements (AIR): are relative to the operation and maintenance of an asset and set out the detailed information needed by the appointing party to effectively manage a physical asset during its lifecycle. During design and construction stages the project AIR will form part of the EIR to deliver related information for asset handover and onward operational management purposes.

Exchange information requirements (EIR): derived from the project and asset information requirements as information to be delivered (exchanged) by respective lead appointed parties to the appointing party (client) at key project delivery milestones. Each EIR is appointment specific and forms part of the invitation to tender pack for each lead appointed party.

  - Required Templates

When delivering these services, the bidder for [insert project name] should adopt the following template documents:

- SFT Standard Information Management Plan (SIMP) version [x]. Refer to links in appendix A.

[Insert link to other documents to be adopted by bidder e.g. SFT SIMP project information strategy dashboard, templates, CAFM import sheets]

# Scope of Works

The information manager will play a key role in supporting the client / contracting authority implement and successfully deliver the Standard information management plan (SIMP) in accordance with BS EN ISO 19650 parts 1 and 2.  To support the appointment process this scope of services has included a range of principle tasks to be delivered at key stages of the project.

One principle task is to ensure the project SIMP is aligned to the client/ contracting authority’s project information requirements (PIR) and then apportioned for each lead appointed party appointment, as illustrated below.

The scope of services seeks to ensure four high level deliverables: -

- support the client establish a project SIMP including project and asset related information requirements.

- develop and manage sets of project information requirements for each lead appointing party for inclusion within each appointment.

- validate the project team’s information deliverables at key delivery milestones.

- enable the delivery of accurate as-built digital information models, a project asset register, O&M manual including Health & Safety information to support lifecycle asset management.

Appendix B includes an Information management assignment matrix which outlines standard information tasks to be performed on a project in accordance with BS EN ISO 19650-2, Annex A. In conjunction, the below table sets out a range of tasks to be delivered by the client information manager on this project:

| 1.0 Project Standard Information Management Plan (SIMP) Establishment of the project SIMP incorporating the project information strategy dashboard, Project and Asset workbooks, and relevant templates. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Task |  | Notes |  |
| 1.1 | Review and update the preliminary project information strategy dashboard (appendix C herein) in collaboration with the contracting authority/ appointing party. |  | One meeting |  |
| 1.2 | Engage early with client/authority stakeholders to enable the development and population of the project Standard information management plan workbooks and templates. The stakeholders include client delivery teams, project managers, estate, facility and/ or asset management teams. In accordance with BS EN ISO 19650-2, the requirements will include clauses 5.1.4: the information standard, 5.1.5: information production methods and procedures, and 5.1.6: reference information and shared resources. These are established as specific items within the SIMP Project Information Requirements Workbook. Identify and communicate any delivery implications, risks, or other issues related to developing the project SIMP workbooks to the relevant stakeholders as early as possible, and work collaboratively to mitigate them. |  | Engagement meeting(s) required |  |
| 1.3 | With reference to 1.2 above, support the development and specification of the high-level Project Information Requirements and associated Exchanges Information Requirements within the SIMP workbook, appendix A1. Ensure the PIR and EIR’s are aligned to the project key decision points and correspond to agreed information delivery milestones. [Utilise SIMP PIR workbook, templates T2, T5 and T6] |  | (e.g. RIBA stages) |  |
| 1.4 | With reference to 1.2 above, support the development and specification of the Asset Information Requirements (AIR), including the project information handover strategy, post information handover set-up, digital O&M manual requirements, asset data deliverables (COBie), asset grading criteria, and a baseline project asset list to inform the final as-completed asset register. During the stakeholder engagement meetings ensure the project room/ space and asset naming conventions are captured and recorded within the SIMP PIR workbook, section 4.1. Adopt the SFT project naming conventions if the client authority does not have an established approach. When developing and supporting the delivery of the project asset register workbook, review the associated SFT asset register task matrix, which structures the tasks, stakeholder dependencies and projects stages for task completion. [Utilise SIMP Asset Register workbook, Project asset naming conventions, associated task matrix, templates T3 and T4] |  | Engagement meeting(s) required |  |
| 1.5 | Work with the contracting authority / appointing party to establish the project information handover strategy and delivery criteria. This will include, but not limited to, the information deliverables exchange, hosting environment, asset register format, 2D/ 3D classification assignment, asset-space naming and onward asset data integration into existing technology platforms; e.g. CAFMs. Record this within the project SIMP workbook so all stakeholders are aware of what has been agreed. |  |  |  |
| 1.6 | In accordance with BS EN ISO 19650-2, clause 5.1.8 support the contracting authority / appointing party establish the Project’s information protocol [include this task if a Project information protocol is not already established by the contracting authority / appointing party. Option to utilise UK BIM framework Information protocol template/ SIMP Template 1] |  |  |  |
| 2.0 Project common data environment strategy (CDE) In accordance with BS EN ISO 19650-2, clause 5.1.7, work with the contracting authority / appointing party to establish the project CDE. The CDE should be informed by Section 4.0 of the fully populated and updated project information strategy dashboard (task 1.1). The SIMP workbook and relevant appendices/ templates should be updated to record the outcomes and requirements. |  |  |  |  |
| Ref |  | Task |  | Notes |
| 2.1 |  | Working with the contracting authority / appointing party: establish a high-level project CDE strategy to suit all project stages and procurement route. Consider technology hosting, management, security, licensing, and IT support requirements.[Refer to item 4.5, SIMP PIR workbook. Utilise SIMP template T2] |  | This should include the adoption of template T2 - Appointing Party Information Container Hierarchy for client information exchange and storage. |
| 2.2 |  | With reference to 2.1 above, establish the appointing party and lead appointed party’s accessibility requirements during the design, construction, handover, and operational phases. |  |  |
| 2.3 |  | With reference to 2.1 above, establish the approach for sharing and approving information containers between the appointing party / lead appointed parties at each project information delivery milestone. [Refer to item 5.1 and 5.2, SIMP PIR workbook.] |  |  |
| 2.4 |  | With reference to 2.1 above, collaborate with the contracting authority / appointing party and contractor to test the agreed information delivery and handover strategy. This should include the test exchange of files, documents and metadata transfer from the contractor to clients CDE (Common Data Environment) or other cloud-based document management systems. Ensure this is completed at the earliest opportunity following the contractors appointment. Support the resolution of any arising quality or technical delivery issues discovered through the test exchanges. |  |  |
| 3.0 Exchange information requirements for each lead appointed party In accordance with BS EN ISO 19650-2, clause 5.2.1 establish the exchange information requirements for each lead appointed party (LAP) and appointment. Assume [XX] number of LAP’s based on the populated and updated project information strategy dashboard (task 1.1) |  |  |  |  |
| Ref |  | Task |  | Notes |
| 3.1 |  | Work with the contracting authority / appointing party to establish the project exchange information requirements for each lead appointed party at each information delivery milestone. Update the SIMP PIR workbook, appendix A1. |  | Engagement meeting(s) required |
| 3.2 |  | Support the contracting authority / appointing party to establish prospective lead appointed parties tender pack(s) including the response requirements and evaluation criteria. |  |  |
| 3.3 |  | Support the contracting authority / appointing party review of tender responses from each lead appointed party (including the pre-appointment BEP) and advise on compliance and suitability. |  |  |
| 3.4 |  | Support the contracting authority / appointing party review of the required appointment level information (including the BEP) received from each lead appointed party and their delivery team(s) and advise on compliance and suitability. |  |  |
| 4.0 Information delivery milestones – Information (model) review & acceptance Review the information deliverables for each lead appointing party in accordance with BS EN ISO 19650-2, clause 5.7.4. This appointment incorporates [xx] project information delivery milestones. The information manager does not complete a design or technical review of the received information rather a compliance audit (check) against (but not limited to) tasks 4.1 - 4.6 below. A benchmark criteria should be developed for completing the project stage audits and reports. |  |  |  |  |
| Ref |  | Task |  | Notes |
| 4.1 |  | - Project information methods and procedures |  |  |
| 4.2 |  | - Project information standard. Ensure the level of Uniclass classification, space - asset naming assignment is compliant to the project information standard. SIMP PIR workbook items 4.1 and 4.3. |  |  |
| 4.3 |  | - Exchange Information requirements (Including the correct handover of information in accordance with SIMP Template – T2 and project model(s) compliance and assurance checks) |  |  |
| 4.4 |  | - agreed acceptance criteria for each information requirement |  |  |
| 4.5 |  | - level of information need for each information requirement (including COBie data population and quality compliance checks) |  |  |
| 4.6 |  | - deliverables listed in the Master information delivery plan |  |  |
| 4.7 |  | Identify non-compliance issues and report to the relevant lead appointed party to allow them to amend and re-submit for acceptance. |  |  |
| 4.8 |  | Track any identified non-compliant issues until they are resolved. |  |  |
| 4.9 |  | Provide regular report(s) to the contracting authority / appointing party outlining review outcomes and compliance across all lead appointed party deliverables. |  |  |
| 4.10 |  | Provide a model and data quality report for prospective tendering contractors, pre-contract award. |  |  |
| - Project completion and handover – Information (model) review & acceptance In accordance with BS EN ISO 19650-2, clause 5.8 review and check compliance of the handover project information model for archive and operational purposes. |  |  |  |  |
| Ref |  | Task |  | Notes |
| 5.1 |  | Review the handover information deliverables from each lead appointed party and check compliance as outlined in section 4.0 above. |  |  |
|  |  | Review the handover deliverables from each lead appointed party and check compliance against the SIMP project, asset and exchange information requirements. [Refer to item 4.8, SIMP PIR workbook.] |  |  |
| 5.2 |  | Support the contracting authority / appointing party in establishing the asset information model and post information handover set-up outlined in section 1.4 above. |  |  |
| 6.0 Capture lessons learnt |  |  |  |  |
| Ref |  | Task |  | Notes |
| 6.1 |  | Work with the contracting authority / appointing party to capture lessons learnt during the project and record them in the project CDE for sharing to SFT and to be called upon by future projects. |  |  |
| 7.0 Additional supplementary services |  |  |  |  |
| Ref |  | Task |  | Notes |
| x.x |  | e.g. attend all/ any soft landings meetings to ensure compliance with information deliverables. |  | [Subject to review and removal as required] |
| x.x |  | e.g. develop Organisation’s information requirements. |  |  |
| x.x |  | e.g. host and manage the client CDE. |  |  |
| x.x |  | Add additional scope as required |  |  |

5.0	Quotation Submission and Evaluation Criteria

[The contracting authority can define submission requirements and evaluation criteria in line with their own tender process and best practice. The following sections offers indicative criteria for consideration]

The submission requirements are as follows:

  - Consultants methodology, understanding, tools and techniques used to deliver the outputs – Maximum 4 pages

Outline your approach to the commission and how you would propose to deliver the information management services set out within the scope of this document.

Outline your organisational experience of applying similar client project information management services on projects in alignment with BS EN ISO 19650 parts 1 and 2: Information management using BIM and / or the SFT Standard Information Management Plan.

Provide two client references who can be contacted to verify.

  - Consultants personnel, experience, and availability – Maximum 4 pages

Provide CVs / profiles of the project information management personnel you are proposing to undertake and deliver the services, outlining relevant skills and experience of similar BIM and information management consultancy work, including any relevant qualifications and training.

Provide a statement of availability for the key personnel proposed, detailing any other significant commitments during this timeframe.

  - Consultants programme & risk register– Maximum 2 pages

Develop an indicative delivery programme and risk register including any proposed mitigation measures.

Provide a table of proposed resource allocation against key activities.

Provide a fee as per pricing requirements in section 6.0.

The submission should be a maximum of [10] pages excluding any cover, content page, fee pages and supporting evidence/ case studies if required.

  - Evaluation Criteria

| Technical |  |  |
| --- | --- | --- |
| Evaluation: 70% weighting |  |  |
| The technical submission should be a maximum of [10] A4 (Font size Arial 12) pages excluding any cover, content page, fee pages and supporting evidence/ case studies if required. |  |  |
| Evaluation Criteria |  | Weighting |
| 1 | Consultants methodology, understanding, tools and techniques used to deliver the outputs. | 30% |
| 2 | Consultants personnel & experience and availability | 30% |
| 3 | Consultants programme & risk register | 10% |
| Commercial |  |  |
| Evaluation: 30% weighting |  |  |

- Fee Proposal

All fees and rates must be submitted net of VAT.

  - Hourly Rates

An hourly rate for each staff member must be provided. This will be the basis of payment for any instructions agreed for any additional work activities out with the scope of the tender.

| Hourly Rate (£) |  |  |  |
| --- | --- | --- | --- |
| Client project information management personnel | Role | Name | Rate (£) |
| Director/Partner |  |  |  |
| Associate Director |  |  |  |
| Associate |  |  |  |
| Other |  |  |  |

  - Fixed Price

A fixed price for each of the task table sections outlined in 4.0 Scope of services.

| Tasks |  | Price (£) |
| --- | --- | --- |
| 1.0 | Project Standard Information Management Plan |  |
| 2.0 | Project common data environment strategy |  |
| 3.0 | Exchange information requirements for each Lead appointed party |  |
| 4.0 | Information delivery milestones – Information review & acceptance |  |
| 5.0 | Project completion and handover – Information review & acceptance |  |
| 6.0 | Capture lessons learnt |  |
| 7.0 | Additional supplementary services [Subject to review and removal as required] |  |
| Total Lump Sum Submission Price (£) |  | Price (£) |
| Lump sum fee |  |  |

Appendix A – SIMP resource arrangement

Appendix B – Information management assignment       matrix

Appendix C – Project information strategy dashboard

[Add preliminary project information strategy dashboard here]

Appendix D – Terms & Conditions

[Add any contracting authority T&C here]